## Sheet1
PROJECT MENTOR FINDER PRODUCT BACKLOG
No | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Status
| Project Documents |  | Complex | Every Iteration | HE150691,HE150600,HE150816,HE150432,HE150692 | Every members in team | Done
| All frontend design + base code |  | Complex | Every Iteration | HE150816 | Trần Nguyễn Thái An | Done
1 | Sign-up | Public | Complex | Iteration 1 | HE150692,HE150816 | Vũ Duy Hà (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
2 | Sign-in | Public | Complex | Iteration 1 | HE150692,HE150816 | Vũ Duy Hà (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
3 | Log out | Public | Simple | Iteration 2 | HE150692,HE150816 | Vũ Duy Hà (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
4 | View profile of an User | Public | Medium | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
5 | Change Password | Common | Simple | Iteration 2 | HE150816,HE150816 | Trần Nguyễn Thái An (Front-end and Back-end) | Done
6 | User Authorization | Common | Complex | Iteration 2 | HE150692,HE150816 | Vũ Duy Hà (Back-end) | Done
7 | Update Mentee profile | Mentee | Simple | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
8 | Create request | Mentee | Medium | Iteration 2 | HE150692,HE150816 | Vũ Duy Hà (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
9 | Statistic request by me | Mentee | Medium | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
10 | Update request | Mentee | Medium | Iteration 2 | HE150816 | Trần Nguyễn Thái An (Back-end + Front-end) | Done
11 | View list my Request | Mentee | Simple | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
12 | Delete Request | Mentee | Simple | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
13 | Rate & comment mentor | Mentee | Complex | Iteration 2 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
14 | View mentee list | Admin | Simple | Iteration 2 | HE150432,HE150816 | Nguyễn Minh Hạnh (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
15 | Update mentee info | Admin | Medium | Iteration 2 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
16 | Deactivate/ Activate mentee account | Admin | Simple | Iteration 2 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
17 | Mentor view list request | Mentor | Medium | Iteration 3 | HE150692,HE150816,HE150432 | Vũ Duy Hà (50%Back-end),Trần Nguyễn Thái An (70%Front-end), Nguyễn Thu An(50% Back-end + 30% Front-end) | Done
18 | Update profile of mentor | Mentor | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
19 | View mentee request | Mentor | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
20 | Search mentee request by categories | Mentor | Complex | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
21 | Enroll to a request | Mentor | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
22 | View enrolled requests | Mentor | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
23 | View mentor enrolled request | Mentee | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An (Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
24 | Accept Reject an Enrolled | Mentee | Complex | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
25 | View Enrolled Mentor Profile | Mentee | Simple | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
26 | Notification | User | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
27 | View accepted mentees | Mentor | Medium | Iteration 3 | HE150432,HE150816 | Nguyễn Thu An(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
28 | View mentor list | Admin | Simple | Iteration 3 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
29 | Update mentor info | Admin | Medium | Iteration 3 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
30 | Deactivate/ Activate mentor account | Admin | Simple | Iteration 3 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
31 | Forgot Password | Guest | Complex | Iteration 3 | HE150600,HE150816 | Nguyễn Minh Hạnh(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
32 | Statistic of all user | Admin | Complex | Iteration 3 | HE150691,HE150816 | Nguyen Tran Hoang(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
33 | Add request | Admin | Simple | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
34 | Update request | Admin | Simple | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
35 | View all request | Admin | Medium | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
36 | Request Statistic | Admin | Medium | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 50% Front-end),Trần Nguyễn Thái An (50%Front-end) | Done
37 | Request Dashboard | Admin | Complex | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 60% Front-end),Trần Nguyễn Thái An (40%Front-end) | Done
38 | Request Details | Admin | Medium | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
39 | Request Filter | Admin | Medium | Iteration 3 | HE150691,HE150816 | Nguyễn Trần Hoàng(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
40 | Delete request | Admin | Simple | Iteration 3 | HE150691,HE150816 | Nguyen Tran Hoang(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
41 | Create request | Admin | Simple | Iteration 3 | HE150691,HE150816 | Nguyen Tran Hoang(Back-end + 30% Front-end),Trần Nguyễn Thái An (70%Front-end) | Done
42 | Admin noti user | Admin | Medium | Iteration 3 | HE150691 | Nguyen Tran Hoang(Back-end) | Done
43 | Admin daily report | Admin | Complex | Iteration 3 | HE150691 | Nguyen Tran Hoang(Back-end + Front-end) | Done
44 | Chat System | Mentor, Mentee | Complex | Iteration 3 | HE150692,HE150816 | Vũ Duy Hà (Back-end + 50% Front-end),Trần Nguyễn Thái An (50%Front-end) | Done