## Wx
PROJECT REPORT
Group | 3
Week | <19/07/2021-25/07/2021>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Push most updated code to Github | Completed
2 | Finish Software Requirement Specification (SRS) | Completed
3 | Finish backlog | Completed
4 | Finish Design Document | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code forgot password + Write SRS and Design | Hanh
2 | Code daily report for admin + Write SRS and Design | Hoang
3 | Fix existed bugs on Request, Enrolled, Notification, Profile | Thu An
4 | Edit Some Screen template | Thai An
5
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
Launch project
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| Add team introduction and project discription to README.md on Github | Duy Ha